## L2 Schedule
Schedule for 400kV overhead Transmission Line from Godda APJL to Kahalgaon A to Maithan B LILO Line
Configuration Details |  | 400KV Quad Moose ACSR
Start date of connectivity |  | Responsibility : - Sumit Mehta
SN | Description | Responsibility | Qty. | Unit | Start Date | End Date | Days |  |  |  | 2025
[8 empty] | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Award of Contract (MoU) on AESL (Zero Date) | APJL |  |  |  | 2024-10-10
2 | Award of EPC Contract for T/L | AESL |  |  | 2024-10-10 | 2024-10-20 | 10
3 | Establishment of site office & team mobilization | Vendor/ AESL |  |  | 2024-10-10 | 2024-10-20 | 10
4 | Engineering activities incl Tower Testing & Approvals | AESL |  |  | 2024-10-01 | 2024-10-10 | 9
a | Submission & Approval of Sag Tension Charts and Tower Spotting Data | AESL |  |  | 2024-10-10 | 2024-10-15 | 5
b | Submission & Approval of Tower Designs for D/C and M/C Towers in line with approved DBR from concern Authority | AESL/APJL |  |  |  |  | 0
c | Submission & Approval of GA, GTP, TTR of Insulator, Conductor, Hardware and Accessories from concern Authority | AESL/APJL |  |  |  |  | 0
d | Submission & Approval of Soil Investigation reports & Foundation drawings | AESL |  |  |  |  | 0
e | Submission & Approval of Structural, Fabrication and Shop Floor Drawings from concern Authority | AESL/APJL |  |  |  |  | 0
f | Proto Assembly and Type Testing of D/C and M/C Towers and Submission of Reports from concern Authority for approval | AESL/APJL |  |  |  |  | 0
g | Approval of Proto Assembly and Type Testing of D/C and M/C Towers and Submission of Reports from concern Authority for approval | AESL/APJL |  |  |  |  | 0
h | Completion of Tower Testing for all type of Towers | AESL |  |  |  |  | 0
5 | Supply Works | [5 empty] | 0
a | Stubs and Earthing | Vendor | 1 | Lot | 2024-12-01 | 2024-12-30 | 29
b | Towers Incl Bolts & Nuts | Vendor |  | Nos | 2025-01-01 | 2025-01-30 | 29
c | Conductor, OPGW, Earthwire and Line Hardware Fittings | Vendor |  | Kms | 2025-01-01 | 2025-01-30 | 29
6 | Preparation , Submission & approval of Statutory Proposal | [5 empty] | 0
a | Section 68 |  |  |  | 2024-10-10 | 2024-11-20 | 41 | [8 empty] | Will apply on 14/10/2024
b | Section 164 |  |  |  | 2024-10-10 | 2025-01-20 | 102 | [8 empty] | 2024-10-30
c | PTCC, BSNL |  |  |  | 2024-12-01 | 2025-02-28 | 89
d | Power Line Crossings | AESL/ APJL | 3 | Nos | 2024-12-01 | 2025-01-15 | 45
7 | Service Works
a | ROW Clearance | AESL/ APJL |  |  | 2024-11-01 | 2025-03-30 | 149
b | Check Survey | Vendor |  | Km. | 2024-11-01 | 2024-11-10 | 9
c | Soil investigation | Vendor |  | Loc | 2024-11-10 | 2024-11-18 | 8
d | Tower Foundation incl Earthing | Vendor |  | Nos. | 2024-12-15 | 2025-02-15 | 62
e | Erection of towers | Vendor |  | Nos. | 2025-01-15 | 2025-03-05 | 49
f | Stringing Inc Earthwire, accessories | Vendor |  | Km. | 2025-02-01 | 2025-03-15 | 42
g | OPGW | Vendor |  | Km. | 2025-03-01 | 2025-03-20 | 19 | bar: 2025 Mar 6 to 2025 May 8
8 | Final Tapping & Commissioning | Vendor/ AESL | 100% | % | 2025-03-20 | 2025-03-30 | 10
NOTE: |  | Monsoon
1 | [5 empty] | MOU between APL & AESL
| Railway Crossing | 0 |  | Nos |  | Total LILO distance: 7.27kM
| NH Crossing | 0 |  | Nos |  | Tower Quantity: 29-Nos
| Power Line Crossing | 3 |  | Nos |  | 132kV Line crossing: 2-Nos
[6 empty] | 400kV Line crossing: 3-Nos |  | 2025 Apr 7: For AESL
Formulas:
End Date = [Start Date]+8